## Project Portfolio Dashboard
PROJECT PORTFOLIO DASHBOARD
DELIVERY TIMELINE & RESOURCES
PROJECT FINANCIALS
RISK ANALYSIS
OPEN & PENDING ACTIONS
PROJECT REPORT
PROJECT NAME | SCHEDULE | BUDGET | RESOURCES | RISKS | ISSUES | COMMENTS
Project A
Project B
Project C
Project D
Project E
Project F
Project G
Project H
Project J
Project K
Project L
Project M
Project N
Project P

## Portfolio Data
PROJECT PORTFOLIO DATA
PROJECT NAME | TIMELINE |  |  |  | NUMBER OF TEAM MEMBERS | BUDGET |  |  | RISKS |  |  | OPEN |  | PENDING ACTIONS
| CALENDAR | BEGIN | FINISH | # of DAYS |  | PROJECTED | ACTUAL | REMAINDER | HIGH | MEDIUM | LOW | ISSUES | REVISIONS
Project A | 2016-05-01 | 2016-05-05 | 2016-07-01 | 57 | 10 | 1000000 | 880000 | 120000 | 1 | 0 | 4 | 2 | 0 | 4
Project B | 2016-06-01 | 2016-05-10 | 2016-08-10 | 92 | 5 | 900000 | 920000 | -20000 | 2 | 3 | 5 | 1 | 2 | 3
Project C | 2016-07-01 | 2016-06-10 | 2017-03-01 | 264 | 10 | 860000 | 850000 | 10000 | 3 | 4 | 3 | 2 | 1 | 2
Project D | 2016-08-01 | 2016-06-22 | 2016-08-04 | 43 | 5 | 1000000 | 998050 | 1950 | 5 | 8 | 1 | 1 | 0 | 0
Project E | 2016-09-01 | 2016-07-14 | 2016-11-01 | 110 | 10 | 294000 | 280000 | 14000 | 8 | 6 | 4 | 0 | 3 | 1
Project F | 2016-10-01 | 2016-07-14 | 2017-01-20 | 190 | 5 | 123400 | 125000 | -1600 | 5 | 0 | 0 | 2 | 0 | 2
Project G | 2016-11-01 | 2016-08-01 | 2016-10-01 | 61 | 10 | 250500 | 246000 | 4500 | 6 | 4 | 0 | 1 | 2 | 3
Project H | 2016-12-01 | 2016-08-14 | 2016-08-30 | 16 | 5 | 127200 | 126000 | 1200 | 7 | 3 | 3 | 0 | 1 | 4
Project J | 2017-01-01 | 2016-09-01 | 2016-12-10 | 100 | 10 | 80000 | 79900 | 100 | 0 | 2 | 4 | 1 | 3 | 2
Project K | 2017-02-01 | 2016-10-01 | 2016-11-15 | 45 | 5 | 77000 | 77000 | 0 | 4 | 4 | 5 | 2 | 0 | 0
Project L | 2017-03-01 | 2016-10-01 | 2016-12-01 | 61 | 10 | 65000 | 65000 | 0 | 3 | 6 | 4 | 3 | 2 | 0
Project M | 2017-04-01 | 2016-11-01 | 2016-12-01 | 30 | 5 | 550000 | 551000 | -1000 | 2 | 3 | 6 | 0 | 1 | 1
Project N | 2017-05-01 | 2016-11-10 | 2016-12-10 | 30 | 10 | 45000 | 42000 | 3000 | 1 | 1 | 7 | 1 | 0 | 2
Project P | 2017-06-01 | 2016-12-01 | 2017-02-10 | 71 | 5 | 32500 | 33000 | -500 | 5 | 0 | 2 | 2 | 1 | 3
[6 empty] | 5404600 | 5272950 | 131650 | 52 | 44 | 48 | 18 | 16 | 27