## ProjectTaskList
PROJECT TASK LIST
{42}
|  | Project Start | 2017-01-01
PROJECT | TASK | PRIORITY | START | PLAN END | ACTUAL END | % COMPLETE | Project Start | Days to Start | Complete | Incomplete | Slippage | Plan Days
Project 1 | Task 1 Description | HIGH | 2017-01-05 | 2017-01-15 | 2017-01-15 | 50% | 2017-01-01 | 4 | 5 | 5 | 0 | 10
| Task 2 Description | MEDIUM | 2017-01-10 | 2017-01-17 | 2017-01-23 | 100% | 2017-01-01 | 9 | 7 | 0 | 6 | 7
Project 2 | Task 1 Title | LOW | 2017-02-15 | 2017-02-28 | 2017-03-10 | 30% | 2017-01-01 | 45 | 3.9 | 9.1 | 10 | 13
| Task 2 Title | HIGH | 2017-01-07 | 2017-02-01 | 2017-02-05 | 50% | 2017-01-01 | 6 | 12.5 | 12.5 | 4 | 25
Project 3 | Task A | LOW | 2017-02-15 | 2017-02-18 |  | 30% | 2017-01-01 | 45 | 0.9 | 2.1 | 0 | 3
| Task B | LOW | 2017-02-25 | 2017-03-07 |  |  | 2017-01-01 | 55 | 0 | 10 | 0 | 10
| Task C | LOW | 2017-03-10 | 2017-03-22 |  |  | 2017-01-01 | 68 | 0 | 12 | 0 | 12
[7 empty] | 2017-01-01 | 0 | 0 | 0 | 0 | 0
[7 empty] | 2017-01-01 | 0 | 0 | 0 | 0 | 0
Insert new rows above this one
[42]
Formulas:
PLAN END = [START]+10
ACTUAL END = [PLAN END]

## Help
HELP
Adjust the Minimum Bound for the X-axis
When you change the Project Start date, you will need to also update the Minimum bound for the X-axis in the gantt chart. Right-click on the x-axis labels in the chart and go to Format Axis.
Adding More Rows
When you insert new rows, you should insert a blank row, then copy formulas down in the columns with the gray background.
Conditional Formatting
The Priority column uses conditional formatting to highlight cells differently based on their text value. If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.